## Sheet1
AIRLINE RESERVATION SYSTEM
TL: Aman Kumar Singh |  |  |  | Team Members : Khushi Mishra Arhan das Mohit Agrawal
User Story | To Do | Doing | Impediments | To-Verify | Done
Program Flow |  |  |  |  | Understand the complete flow of the project
Database Design |  |  |  |  | Decide the tables and relations among them required by the project
Project setup |  |  |  |  | Create a project on Github and make the team members a collaborator
Database Creation |  |  |  |  | Create the designed Database on MS-SQl
Home page Component |  |  |  |  | Create the home page component with Login, Register, Flight search interface using CSS/Bootstrap/angular material (Mohit)
Search Result |  |  |  |  | Show result for Flight search (Arhan)
Register User |  |  |  |  | Create Register page for a new user and take required inputs (validate) . (Same style as home page) POST method in backend User Repo (Khusi)
Login User |  |  |  |  | Create Login page for a registered user , take required inputs and validate login credentials from DB . (Same style as home page) LOGIN SERVICE Login interface (Khushi)
Login Admin |  |  |  |  | Create Login page for Admin , take required inputs ( Email, password) and validate credentials . (Aman)
Add Flight (Admin) |  |  |  | Create Add Flight (with date) page for Admin POST method (Aman)
Delete Flight(Admin) |  |  |  |  | Create Delete page for Admin DELETE method (mohit)
Auth Guards/Route Guard |  |  |  | Limit Access to user and admin (Aman)
Seat Select (User) |  | Create a seat matrix to show to user the available and booked seats when the user selects a flight.
Passenger |  |  |  |  | Enter Passenger details (form) Local Storage (mohit)
Payment (User) |  |  |  |  | Create a payment page and method for a user who has selected seat(s) for a flight and wants to book the seats. PAYMENT SERVICE Dummy Entries
Ticket Print (User) | Create a method to print booked tickets PRINT SERVICE GET method to print in frontend Ticket Layout
Ticket Cancellation (User) | Create a ticket cancellation page for User and check for booking details to cancel a booked ticket Cancelled Ticket Layout
Print Cancelled Ticket(User) | Make a component to show cancelled ticket and an option to print the cancelled ticket
Forgot Password (User) |  |  |  |  | FORGOT PASSWORD SERVICE PUT method in backend (khushi)
Password Validation, confirm password , frontend validations (mobile) |  |  |  |  | Strong Password, Confirm Password (Register page) (Arhan)
Admin View |  |  |  | Show all flights and option to delete or add flight
User Profile |  |  |  | Show Booking History and option to cancel ticket
Finalize Templates
Finalize Routes
Finalize Validations
Auto Calculate Age , Duration ; Add flight- Autogenerate ID
3hrs